## Sheet1
Requirement ID | Requirement Details | Status Code | Comments
1 | Bluetooth Multiplayer | P | Connection sucessful, but key functions do not perform. Currently not supported
2 | Adventures/Quests | D | Plot order works outside of bluetooth
3 | Randomized Adventure | D | Follows strict plot, but has segments of randomly chosen battles/inconsequential decision events
4 | Character Models | D
5 | Enemy Models | D
6 | Use Unity Game Engine | A | Discovered very early on this wasn't the way to go
7 | Character Classes/Stats/Abilities | D
8 | Music | D
9 | Graphics | D
10 | SurfaceView for Character Animation | A | Story Module uses static images, conflicts with Battle Module during activity switching
11 | Game End Condition | D
12 | Character Progression | A | Characters have stats, but stat progression abandoned during scope reduction
13 | User Interface | D
14 | Battle System | D | Abilities work outside of Bluetooth
15 | Gameplay Length Choice | A | Abandoned during scope reduction